## Лист1
Week | Task Name | Description | Start Date | Finish Date | Responsible Members | Status
1 | Week
| Project Proposal | Word file with main idea | 5 April | 12 April | ALL | Completed
2 | Week
| Project Plan | Main Structure of Site Distribution of tasks among members Create Repository in Github | 12 April | 18 April | ALL | Completed
3 | Week
| Home Page Frontend | Make main page Header, Footer and Content | 19 April | 22 April | Almas, Kadyrali
| Log/Reg frontend and backend | Create <input> tags, and proccess it | 23 April | 25 April | Zhanibek, Riyat
4
| Database management | Make database and PHP connection, or Node.js | 26 April | 2 May | Zhanibek, Riyat
| Search button Front and Backend |  | 26 April | 2 May | Almas, Kadyrali
5
| User profile page front-end |  | 3 May | 9 May | Kadyrali, Zhanibek
6
| Movie page front-end |  | 10 May | 16 May | Almas, Riyat
7
| Dynamic User and Movie |  | 17 May | 23 May | Zhanibek, Almas
8
| Add to Cart, Like, Comments button front-end |  | 24 May | 30 May | Kadiraly, Riyat
9
| Payment system backend |  | 31 May | 6 June | Zhanibek, Almas
| Payment system backend |  | 31 May | 6 June | Kadiraly, Riyat
10
| Additional details |  |  |  | ALL